## Summary
Metric | Value
Project Name | PlanIFlow V3 Development
Project Start Date | 2026-01-01T08:00:00
Project End Date | 2026-02-14T17:00:00
Working Hours Start | 08:00
Working Hours End | 16:00
Total Tasks | 13
Summary Tasks | 4
Work Tasks | 9
Total Resources | 7
Overall % Complete | 43.4%
Total Project Duration (days) | 45
Export Date | 2026-01-14 03:48:44
File Version | 2.3
Date Format | yyyy-mm-dd
Currency | USD
Total Project Cost | $27472.00

## Tasks
Task ID | WBS | Task Name | Type | Schedule Mode | Level | Parent ID | Is Summary | Is Milestone | Start Date | End Date | Duration (days) | % Complete | Status | Status Color | Predecessors | Assigned Resources | Notes | Font Family | Font Size | Font Color | Background Color | Font Bold | Font Italic | Font Underline
1 | 1 | PlanIFlow V3 Project | Summary | Auto | 0 |  | Yes | No | 2026-01-01T08:00:00 | 2026-02-14T17:00:00 | 31 | 40 | In Progress | green |  |  | Main project container |  |  | #000000 | #FFFFFF | Yes | No | No
2 | 1.1 | Phase 1: Initiation | Summary | Auto | 1 | 1 | Yes | No | 2026-01-01T08:00:00 | 2026-01-07T17:00:00 | 4 | 100 | Completed | blue | [5 empty] | #000000 | #FFFFFF | Yes | No | No
3 | 1.1.1 | Kickoff Meeting | Milestone | Auto | 2 | 2 | No | Yes | 2026-01-01T08:00:00 | 2026-01-01T08:00:00 | 0 | 100 | Completed | blue |  | Manager (100%) | Start of project |  |  | #000000 | #FFFFFF | No | Yes | No
4 | 1.1.2 | Gather Requirements | Task | Auto | 2 | 2 | No | No | 2026-01-02T08:00:00 | 2026-01-07T17:00:00 | 4 | 100 | Completed | blue | 3 (Finish-to-Start) | Analyst (100%), Manager (20%) | Interviews with stakeholders |  |  | #000000 | #FFFFFF | No | No | No
5 | 1.2 | Phase 2: Development | Summary | Auto | 1 | 1 | Yes | No | 2026-01-08T08:00:00 | 2026-01-28T17:00:00 | 15 | 60 | In Progress | green | 4 (Finish-to-Start) |  |  |  |  | #000000 | #FFFFFF | Yes | No | No
6 | 1.2.1 | Frontend Architecture | Task | Auto | 2 | 5 | No | No | 2026-01-08T08:00:00 | 2026-01-14T17:00:00 | 5 | 100 | Completed | blue |  | Senior Dev (100%) | Choosing framework |  |  | #000000 | #FFFFFF | No | No | No
7 | 1.2.2 | Backend DB Design | Task | Auto | 2 | 5 | No | No | 2026-01-08T08:00:00 | 2026-01-12T17:00:00 | 3 | 100 | Completed | blue |  | Backend Dev (100%) |  |  |  | #000000 | #FFFFFF | No | No | No
8 | 1.2.3 | Implement API | Task | Auto | 2 | 5 | No | No | 2026-01-13T08:00:00 | 2026-01-20T17:00:00 | 6 | 50 | In Progress | green | 7 (Finish-to-Start) | Backend Dev (100%) | Delay expected here |  |  | #000000 | #FFFFFF | No | No | No
9 | 1.2.4 | Implement UI Components | Task | Auto | 2 | 5 | No | No | 2026-01-15T08:00:00 | 2026-01-28T17:00:00 | 10 | 30 | Upcoming | grey | 6 (Finish-to-Start) | Junior Dev (100%), Senior Dev (50%) |  |  |  | #000000 | #FFFFFF | No | No | No
10 | 1.3 | Phase 3: Testing | Summary | Auto | 1 | 1 | Yes | No | 2026-01-29T08:00:00 | 2026-02-14T17:00:00 | 12 | 0 | Upcoming | grey | 9 (Finish-to-Start), 8 (Finish-to-Start) |  |  |  |  | #000000 | #FFFFFF | Yes | No | No
11 | 1.3.1 | Integration Testing | Task | Auto | 2 | 10 | No | No | 2026-01-29T08:00:00 | 2026-02-04T17:00:00 | 5 | 0 | Upcoming | grey |  | Tester (100%) |  |  |  | #000000 | #FFFFFF | No | No | No
12 | 1.3.2 | Bug Fixes | Task | Auto | 2 | 10 | No | No | 2026-02-05T08:00:00 | 2026-02-11T17:00:00 | 5 | 0 | Upcoming | grey | 11 (Finish-to-Start) | Senior Dev (100%) |  |  |  | #000000 | #FFFFFF | No | No | No
13 | 1.4 | Deployment | Task | Auto | 1 | 1 | No | No | 2026-02-12T08:00:00 | 2026-02-14T17:00:00 | 2 | 0 | Upcoming | grey | 12 (Finish-to-Start) | DevOps (100%) | Go Live! |  |  | #000000 | #FFFFFF | No | No | No

## Resources
Resource Name | Max Hours/Day | Total Hours Allocated | Tasks Assigned | Billing Rate ($/hr) | Total Amount ($) | Exceptions
Manager | 8 | 6.4 | 1 | 80 | 512
Analyst | 8 | 32 | 1 | 60 | 1920
Senior Dev | 8 | 116 | 3 | 100 | 11600 | 2026-01-16
Backend Dev | 8 | 72 | 2 | 90 | 6480
Junior Dev | 8 | 80 | 1 | 40 | 3200
Tester | 8 | 40 | 1 | 50 | 2000
DevOps | 8 | 16 | 1 | 110 | 1760

## Status Breakdown
Status | Count
Completed | 4
In Progress | 1
Upcoming | 4

## Dependencies
Dependency Type | Count
Finish-to-Start | 8

## BL_Initial Plan
Task ID | Task Name | WBS | Start Date | End Date | Duration | % Complete
1 | PlanIFlow V3 Project | 1 | 2026-01-01T08:00:00 | 2026-02-10T17:00:00 | 30 | 0
2 | Phase 1: Initiation | 1.1 | 2026-01-01T08:00:00 | 2026-01-07T17:00:00 | 5 | 0
3 | Kickoff Meeting | 1.1.1 | 2026-01-01T08:00:00 | 2026-01-01T08:00:00 | 0 | 0
4 | Gather Requirements | 1.1.2 | 2026-01-02T08:00:00 | 2026-01-07T17:00:00 | 4 | 0
5 | Phase 2: Development | 1.2 | 2026-01-08T08:00:00 | 2026-01-25T17:00:00 | 12 | 0
6 | Frontend Architecture | 1.2.1 | 2026-01-08T08:00:00 | 2026-01-12T17:00:00 | 3 | 0
7 | Backend DB Design | 1.2.2 | 2026-01-08T08:00:00 | 2026-01-12T17:00:00 | 3 | 0
8 | Implement API | 1.2.3 | 2026-01-13T08:00:00 | 2026-01-18T17:00:00 | 4 | 0
9 | Implement UI Components | 1.2.4 | 2026-01-13T08:00:00 | 2026-01-25T17:00:00 | 9 | 0
10 | Phase 3: Testing | 1.3 | 2026-01-26T08:00:00 | 2026-02-10T17:00:00 | 11 | 0
11 | Integration Testing | 1.3.1 | 2026-01-26T08:00:00 | 2026-01-30T17:00:00 | 4 | 0
12 | Bug Fixes | 1.3.2 | 2026-02-02T08:00:00 | 2026-02-06T17:00:00 | 4 | 0
13 | Deployment | 1.4 | 2026-02-09T08:00:00 | 2026-02-10T17:00:00 | 2 | 0

## Baselines
Baseline Name | Created Date | Tasks Captured
Initial Plan | 2025-12-30T10:00:00 | 13

## Holidays
Holiday Name | Start Date | End Date | Comment
New Year | 2026-01-01 | 2026-01-01 | Happy New Year