## Summary
Metric | Value
Project Name | Project Replica
Project Start Date | 2025-10-30
Project End Date | 2025-11-27
Total Tasks | 7
Summary Tasks | 3
Work Tasks | 4
Total Resources | 2
Overall % Complete | 8.1%
Total Project Duration (days) | 29
Export Date | 2025-10-30 20:05:42
File Version | 2.0

## Tasks
Task ID | Task Name | Type | Level | Parent ID | Is Summary | Is Milestone | Start Date | End Date | Duration (days) | % Complete | Status | Status Color | Predecessors | Assigned Resources | Notes
1 | ▶ Project Name | Summary | 0 |  | Yes | No | 2025-10-30 | 2025-11-27 | 21 | 8 | In Progress | green
2 | ◆ Project Start Milestone | Milestone | 1 | 1 | No | Yes | 2025-10-30 | Milestone | 0 | 100 | Completed | blue |  | Project
3 | ▶ Requirements | Summary | 1 | 1 | Yes | No | 2025-11-19 | 2025-11-27 | 7 | 8 | Upcoming | grey
4 | ▶ Find Scope | Summary | 2 | 3 | Yes | No | 2025-11-19 | 2025-11-27 | 7 | 8 | Upcoming | grey | 2 (Finish-to-Start) | Security,Project
5 | Create Plan | Task | 3 | 4 | No | No | 2025-11-19 | 2025-11-26 | 6 | 10 | Upcoming | grey | 4 (Finish-to-Start) | Security
6 | Get Plan Approval | Task | 3 | 4 | No | No | 2025-11-27 | 2025-11-27 | 1 | 0 | Upcoming | grey | 5 (Finish-to-Start) | Project | Get Approval
7 | ◆ Project End | Milestone | 1 | 1 | No | Yes | 2025-11-28 | Milestone | 0 | 0 | Upcoming | grey | 6 (Finish-to-Start) | Project

## Resources
Resource Name | Max Hours/Day | Total Hours Allocated | Tasks Assigned | Exceptions
Security | 8 | 48 | 1
Project | 8 | 24 | 3

## Status Breakdown
Status | Count
Completed | 1
Upcoming | 3

## Dependencies
Dependency Type | Count
Finish-to-Start | 4