## Summary
Metric | Value
Project Name | Test Project
Project Start Date | 2025-12-09T08:00:00
Project End Date | 2025-12-31T18:00:00
Working Hours Start | 10:00
Working Hours End | 18:00
Total Tasks | 9
Summary Tasks | 2
Work Tasks | 7
Total Resources | 3
Overall % Complete | 0.0%
Total Project Duration (days) | 23
Export Date | 2025-12-12 02:47:55
File Version | 2.3
Date Format | yyyy-mm-dd

## Tasks
Task ID | WBS | Task Name | Type | Schedule Mode | Level | Parent ID | Is Summary | Is Milestone | Start Date | End Date | Duration (days) | % Complete | Status | Status Color | Predecessors | Assigned Resources | Notes | Font Family | Font Size | Font Color | Background Color | Font Bold | Font Italic | Font Underline
1 | 1 | Summary | Summary | Auto Scheduled | 0 |  | Yes | No | 2025-12-09T08:00:00 | 2025-12-31T18:00:00 | 17 | 0 | In Progress | green |  |  |  | Arial | 10 | #000000 | #FFFFFF | Yes | No | No
2 | 1.1 | Milestone 0 | Milestone | Auto Scheduled | 1 | 1 | No | Yes | 2025-12-09T08:00:00 | 2025-12-09T08:00:00 | 0 | 100 | Completed | blue |  |  | Start | Arial | 10 | #000000 | #FFFFFF | No | Yes | No
3 | 1.2 | Task 1 | Task | Auto Scheduled | 1 | 1 | No | No | 2025-12-11T08:00:00 | 2025-12-12T18:00:00 | 2 | 0 | In Progress | green | 2 (Finish-to-Start+2d) | User 1 (100%) | Test Notes | Arial | 10 | #000000 | #FFFFFF | No | No | No
4 | 1.3 | Task 2 | Task | Auto Scheduled | 1 | 1 | No | No | 2025-12-12T10:00:00 | 2025-12-17T18:00:00 | 4 | 0 | Upcoming | grey | 3 (Finish-to-Start-1d) | User 2 (100%) | Test Notes | Arial | 10 | #000000 | #FFFFFF | No | No | No
5 | 1.4 | Milestone 1 | Milestone | Auto Scheduled | 1 | 1 | No | Yes | 2025-12-17T18:00:00 | 2025-12-17T18:00:00 | 0 | 0 | Upcoming | grey | 4 (Finish-to-Start) | User 3 (100%) |  | Arial | 10 | #000000 | #FFFFFF | No | Yes | No
6 | 1.5 | Sub Summary | Summary | Auto Scheduled | 1 | 1 | Yes | No | 2025-12-18T10:00:00 | 2025-12-30T18:00:00 | 9 | 0 | Upcoming | grey |  |  | Test Notes | Arial | 10 | #000000 | #FFFFFF | Yes | No | No
7 | 1.5.1 | Task 3 | Task | Auto Scheduled | 2 | 6 | No | No | 2025-12-18T10:00:00 | 2025-12-26T18:00:00 | 7 | 0 | Upcoming | grey | 5 (Finish-to-Start) |  | Test Notes 2 | Arial | 10 | #de4cca | #FFFFFF | No | No | No
8 | 1.5.2 | Milestone 2 | Task | Auto Scheduled | 2 | 6 | No | No | 2025-12-29T10:00:00 | 2025-12-30T18:00:00 | 2 | 0 | Upcoming | grey | 7 (Finish-to-Start) | User 3 (100%) |  | Arial | 10 | #000000 | #74ff1e | Yes | No | No
9 | 1.6 | Milestone 3 | Milestone | Auto Scheduled | 1 | 1 | No | Yes | 2025-12-31T18:00:00 | 2025-12-31T18:00:00 | 0 | 0 | Upcoming | grey | 6 (Finish-to-Start+1d) | User 3 (100%) |  | Arial | 10 | #000000 | #FFFFFF | No | Yes | No

## Resources
Resource Name | Max Hours/Day | Total Hours Allocated | Tasks Assigned | Exceptions
User 1 | 8 | 16 | 1 | 2025-12-10
User 2 | 8 | 8 | 1 | 2025-12-15 to 2025-12-19
User 3 | 8 | 16 | 1

## Status Breakdown
Status | Count
In Progress | 1
Upcoming | 5
Completed | 1

## Dependencies
Dependency Type | Count
Finish-to-Start | 6

## BL_Baseline 1
Task ID | Task Name | WBS | Start Date | End Date | Duration | % Complete
1 | Summary | 1 | 2025-12-09T08:00:00 | 2025-12-19T16:00:00 | 9 | 0
2 | Task 1 | 1.1 | 2025-12-09T08:00:00 | 2025-12-11T16:00:00 | 3 | 0
3 | Task 2 | 1.2 | 2025-12-12T08:00:00 | 2025-12-16T16:00:00 | 3 | 0
4 | Milestone 1 | 1.3 | 2025-12-16T16:00:00 | 2025-12-16T16:00:00 | 0 | 0
5 | Sub Summary | 1.4 | 2025-12-17T08:00:00 | 2025-12-19T16:00:00 | 3 | 0
6 | Task 3 | 1.4.1 | 2025-12-17T08:00:00 | 2025-12-19T16:00:00 | 3 | 0
7 | Milestone 2 | 1.4.2 | 2025-12-19T16:00:00 | 2025-12-19T16:00:00 | 0 | 0
8 | Milestone 3 | 1.5 | 2025-12-18T16:00:00 | 2025-12-18T16:00:00 | 0 | 0

## Baselines
Baseline Name | Created Date | Tasks Captured
Baseline 1 | 2025-12-09T04:20:35 | 8